## Sheet1
Starting Criteria
Week | 7 | Days
Weekly Work | 5 | Days
Weekly Work | 37 | Hours
Prof Dev Module | 0.25 | Proportion of total year effort
Live Project | 0.55 | Proportion of Prof Dev
Effort |  |  |  | Totals |  |  | For Selection |  | For Selection |  | For Selection
Minimum |  |  |  | 5.0875 | Hours per Week |  | Minimum |  | Term |  | Requirements
Expected | 1 | Extra-curricular hours per night |  | 10.0875 | Hours per Week |  | Expected |  | Non-term |  | Design
Stretch | 2 | Extra curricular hours per night |  | 15.0875 | Hours per Week |  | Stretch |  |  |  | Impl
None
|  | Year | Month | Day
Start Date |  | 2018 | 10 | 29 | 2018-10-29
|  |  | Investigation | [6 empty] | 283.0625
|  |  | Requirements |  |  | 65.9625 | Design |  |  | 217.1 | Implementation | [8 empty] | 309.1125 | Release |  |  | 237.1
Team | Make Progress
|  |  | Term | Term | Term | Term | Term | Term | Term | Non-term | Non-term | Non-term | Term | Term | Term | Term | Term | Term | Term | Term | Term | Term | Term | Term |  | Hours
| Member | Week | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22
|  | Sprint | 0.75 |  | 1.75 |  | 2.75 |  | 3.75 |  | 4.75 |  | 5.75 |  | 6.75 |  | 7.75 |  | 8.75 |  | 9.75 |  | 10.75
|  | Commencing | 2018-10-29 | 2018-11-05 | 2018-11-12 | 2018-11-19 | 2018-11-26 | 2018-12-03 | 2018-12-10 | 2018-12-17 | 2018-12-24 | 2018-12-31 | 2019-01-07 | 2019-01-14 | 2019-01-21 | 2019-01-28 | 2019-02-04 | 2019-02-11 | 2019-02-18 | 2019-02-25 | 2019-03-04 | 2019-03-11 | 2019-03-18 | 2019-03-25 |  | Minimum | Expected | Stretch | Total
| Murtaza |  | None | None | Minimum | Minimum | Minimum | Minimum | Minimum | Stretch | None | None | Minimum | Expected | Minimum | Minimum | Minimum | Minimum | Minimum | Minimum | Minimum | Minimum | Minimum | Minimum |  | 81.4 | 10.0875 | 15.0875 | 106.575
| binarydecoder01 |  | None | None | Minimum | Minimum | Minimum | Expected | Expected | Stretch | None | None | Minimum | Expected | None | Minimum | Expected | Expected | Minimum | Minimum | Stretch | Stretch | Stretch | Stretch |  | 35.6125 | 50.4375 | 75.4375 | 161.4875
| Cole |  | None | None | Expected | Minimum | Minimum | Minimum | Minimum | Stretch | None | None | Minimum | Minimum | Minimum | Minimum | Minimum | Minimum | Minimum | Minimum | Minimum | Minimum | Minimum | Minimum |  | 81.4 | 10.0875 | 15.0875 | 106.575
| gordonj022 |  | None | None | Minimum | Expected | Expected | Expected | Minimum | Stretch | None | None | Minimum | Expected | Minimum | Expected | Expected | Minimum | Expected | Stretch | Stretch | Stretch | Stretch | Stretch |  | 25.4375 | 70.6125 | 90.525 | 186.575
| robflynnyh |  | None | None | Minimum | Minimum | Expected | Minimum | Stretch | Stretch | None | None | Minimum | Expected | Minimum | Expected | Stretch | Minimum | Minimum | Minimum | Expected | Stretch | Stretch | Stretch |  | 40.7 | 40.35 | 90.525 | 171.575
| newGuy |  | None | None | None | Minimum | Minimum | Minimum | Minimum | Stretch | None | None | Minimum | Minimum | Minimum | Minimum | Minimum | Minimum | Minimum | Minimum | Minimum | Minimum | Minimum | Minimum |  | 81.4 | 0 | 15.0875 | 96.4875
|  |  | None | None | None | None | None | None | None | None | None | None | None | None | None | None | None | None | None | None | None | None | None | None |  | 0 | 0 | 0 | 0
|  |  | None | None | None | None | None | None | None | None | None | None | None | None | None | None | None | None | None | None | None | None | None | None |  | 0 | 0 | 0 | 0
|  |  | None | None | None | None | None | None | None | None | None | None | None | None | None | None | None | None | None | None | None | None | None | None |  | 0 | 0 | 0 | 0
|  |  | None | None | None | None | None | None | None | None | None | None | None | None | None | None | None | None | None | None | None | None | None | None |  | 0 | 0 | 0 | 0
| Hours | Minimum | 0 | 0 | 20.35 | 25.4375 | 20.35 | 20.35 | 20.35 | 0 | 0 | 0 | 30.525 | 10.175 | 25.4375 | 20.35 | 15.2625 | 25.4375 | 25.4375 | 25.4375 | 15.2625 | 15.2625 | 15.2625 | 15.2625
|  | Expected | 0 | 0 | 10.0875 | 10.0875 | 20.175 | 20.175 | 10.0875 | 0 | 0 | 0 | 0 | 40.35 | 0 | 20.175 | 20.175 | 10.0875 | 10.0875 | 0 | 10.0875 | 0 | 0 | 0 | Totals | 345.95 | 181.575 | 301.75 | 829.275 | Hours
|  | Stretch | 0 | 0 | 0 | 0 | 0 | 0 | 15.0875 | 90.525 | 0 | 0 | 0 | 0 | 0 | 0 | 15.0875 | 0 | 0 | 15.0875 | 30.175 | 45.2625 | 45.2625 | 45.2625
| Total Hours | Week | 0 | 0 | 30.4375 | 35.525 | 40.525 | 40.525 | 45.525 | 90.525 | 0 | 0 | 30.525 | 50.525 | 25.4375 | 40.525 | 50.525 | 35.525 | 35.525 | 40.525 | 55.525 | 60.525 | 60.525 | 60.525 | Total |  |  | 829.275 |  | Hours
| Total Hours | Sprint | 2018-11-05: 0; 2018-11-19: 65.9625; 2018-12-03: 81.05; 2018-12-17: 136.05; 2018-12-31: 0; 2019-01-14: 81.05; 2019-01-28: 65.9625; 2019-02-11: 86.05; 2019-02-25: 76.05; 2019-03-11: 116.05; 2019-03-25: 121.05 | Total |  |  | 829.275 |  | Hours
You have | 829.275 | Hours, to spend on your project